## all projects
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
Construction Division
PROGRAM OF WORKS | [10 empty] | POW AMOUNT | WORK ORDER |  | IMPLEMENTATION ORDER |  | SOURCE OF FUNDS | DESCRIPTION | LOCATION | IMPLEMENTATION SCHEDULE |  |  | PROGRESS AS OF | [13 empty] | % of Accomplishment | Date Received | Remarks
NO. | DATE | MATERIALS COST | LABOR COST | OVERHEAD COSTS | [6 empty] | TOTAL AMOUNT | NO. | DATE | NO. | DATE |  |  |  | START | FINISH | DURATION (days) | 2021-05-07
|  |  |  | SUP | ENGG SERVICES | SALARIES | FUEL&OIL | Formworks/ Shoring | OTHERS | TOTAL | [11 empty] | STATUS | ACTUAL DATE COMPLETED | running duration (days) | slippage in SCHED | slippage in AMOUNT | OT MAN-HRS | OT AMOUNT | NO. of PR RELEASED | AMT of PR RELEASED | MATERIALS COST | LABOR COST | FUEL & OIL COST | TOTAL AMOUNT used | % to POW
|  | 362155.39 | 83637 |  |  | 7131 | 21360 |  | 103506 | 131997 | 577789.39 | 20-001-A | 2020-01-13 | IO-20-011 | 2020-01-17 | CAPEX 2020 Transmission & Dist. Mains Distribution Lines- Various Sizes | Prop. Extension of 100mm Distribution Line, 200mm Distribution Line w/ 75mm Blow Off Valve | Luminarias St., JR Borja Extn. |  |  | 26 wd = 161 mandays | not started | [14 empty] | recvd 1/20/2020 | waiting for new excavation permit
|  | 1980796.94 | 741419 |  |  | 71484 | 105620 |  | 246587 | 423691 | 3145906.94 | 20-002-A | 2020-01-13 | IO-20-012 | 2020-01-17 | CAPEX 2020 (VEI Projects- Work Package 4, Distribution Line at Tierra del Puerto, Camaman-an) | Prop. 100mm Pipeline Extension with 14 Units 50mm MSO & DMA | Sitio Tierra Del Puerto, Camaman-an |  |  | 102 wd = 1157 mandays | not started | [14 empty] | recvd 1/20/2020
|  | 18129 | 5448 |  |  | 319.65 |  |  |  | 319.65 | 23896.65 | Com2020-003-F | 2020-01-21 | IO-20-018 | 2020-01-30 | CAPEX 2019 (Transmission & Dist. Mains, Meter Stub-out) | Prop. 1-Unit 50mmØ Public Stub-out | Sambaan Village, Patag | 2020-09-12 | 2020-09-12 | 2 wd = 10 mandays | completed | [14 empty] | recvd 2/3/2020
|  | 864420.72 | 198595 |  |  | 35650 | 28538 |  | 21570 | 85758 | 1148773.72 | 20-003-A | 2020-01-15 | IO-20-007 | 2020-01-17 | CAPEX 2020 (VEI Projects- Work Package 4, Water Supply System to Urban/Rural Poor Waterless Communities) | Prop. Rehabilitation of Water Supply System | Macapaya Phase 1A, Camaman-an | June |  | 50 wd = 350 mandays | in progress | [14 empty] | recvd 1/21/2020
|  | 22582 | 16974.27 |  |  | 889.87 | 2750 |  | 23347.34 | 26987.21 | 66543.48 | Com2020-004-F | 2020-01-21 | IO-20-015 | 2020-01-28 | CAPEX 2020 (Transmission & Dist. Mains, Meter Stub-out) | Prop. 1-Unit 50mmØ Public Stub-out | Brgy. 9, Pabayo St. |  |  | 6 wd = 30 mandays | not started | [14 empty] | recvd 1/30/2020
|  | 20540.24 | 18624 |  |  | 2641 | 3850 |  | 20373 | 26864 | 66028.24 | Com2020-004-F | 2020-02-05 | IO-20-026 | 2020-02-10 | CAPEX 2019 (Transmission & Dist. Mains, Meter Stub-out) | Prop. 1-Unit 50mmØ Public Stub-out | JR Borja Extension, Gusa |  |  | 4 wd = 30 mandays | not started | [14 empty] | 2020-02-17
|  | 3236264.04 | 774209 |  | 23669 | 131119 | 93250 |  | 229025 | 477063 | 4487536.04 | 20-004-A | 2020-01-17 | IO-20-014 | 2020-01-22 | CAPEX 2020 (VEI Projects- Work Package 4, Distribution Line at Pamalihi Relocation Site) | Prop. 200mm Pipeline Extension | Mahogany to Pamalihi Relocation Site |  |  | 90 wd = 1108 mandays | not started | [14 empty] | recvd 1/28/2020
|  | 78452 | 26007 |  |  | 1461 | 14850 |  | 11687 | 27998 | 132457 | Com2020-005-F | 2020-02-05 | IO-20-027 | 2020-02-10 | CAPEX 2020 (Transmission & Dist. Mains, Meter Stub-out) | Prop. 1-Unit 50mmØ Public Stub-out | Amfana St., Carmen |  |  | 10 wd = 50 mandays | not started | [14 empty] | 2020-02-17
|  | 267041 | 165593 |  | 252 | 23008 | 47048 |  | 47355 | 117663 | 550297 | 20-005-F | 2020-01-22 | IO-20-016 | 2020-01-28 | CAPEX 2020 Transmission & Dist. Mains Realignment of Pipelines Affected by DPWH Projects | Prop. 400mm Pipe Realignment | J Seriña St., Carmen |  |  | 25 wd = 272 mandays | not started | [14 empty] | recvd 1/30/2020
|  | 36099 | 28290.45 |  |  | 1449.59 | 3850 |  | 25134.38 | 30433.97 | 94823.42 | Com2020-006-F | 2020-02-05 | IO-20-025 | 2020-02-10 | CAPEX 2020 (Transmission & Dist. Mains, Meter Stub-out) | Prop. 1 Unit 50mm Public Stub-out | B3 L2 Ficcoville, Iponan |  |  | 10 wd = 50 mandays | not started | [14 empty] | 2020-02-17
|  | 68814 | 33948.55 |  | 1729.44 |  | 412.5 |  | 8364.56 | 10506.5 | 113269.05 | Com2020-007-F | 2020-02-14 |  |  | capex 2020 | Prop. 1 Unit 50mm Public Stub-out | San Isidro Lumbia | 2020-09-05 | 2020-09-05 | 1 wd | completed | [14 empty] | 2020-04-30
|  | 41305 | 22632.36 |  | 1169.73 |  | 3850 |  | 25759.1 | 30778.83 | 94716.19 | Com2020-009-F | 2020-03-02 |  |  | Capex 2020 | Prop. 1 Unit 50mm Public Stub-out | Zone 1 Igpit Opol |  |  | 8 days | not started | [14 empty] | 2020-04-30
|  | 51119 | 22632.36 |  |  | 1169.73 |  |  | 6179.28 | 7349.01 | 81100.37 | Com2020-10-F | 2020-02-21 |  |  | Capex 2020 | Prop. 2 Unit 50mm Public Stub-out | Tierra de Puerto, Camaman-an, CDO |  |  | 8 wd | not started | [14 empty] | 2020-04-30
|  | 41096 | 23899.73 |  | 1178.82 |  | 5250 |  | 5764.02 | 12192.84 | 77188.57 | Com2020-011-F | 2020-03-02 |  |  | Capex 2020 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia |  |  | 8 wd | not started | [14 empty] | 2020-04-30
|  | 29542 | 11949.86 |  | 614.86 |  | 700 |  | 3695.04 | 5009.9 | 46501.76 | Com2020-012-F | 2020-02-24 |  |  | Capex 2020 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia | 2020-09-26 | 2020-09-26 | 4 wd | completed | [13 empty] | 100% | 2020-04-30
|  | 30351 | 22632 |  | 1169 |  |  |  | 3688 | 4857 | 57840 | Com2020-013-F | 2020-03-05 |  |  | Capex 2020 | Prop. 1 Unit 50mm Public Stub-out | Zone 6, Gawad Kalinga Bugo | 2020-10-17 | 2020-10-17 |  | completed | [13 empty] | 100%
|  | 123506 | 59244 | 451 | 296 | 9720 | 13614 |  | 15628 | 39709 | 222459 | 20-006-A | 2020-01-23 | IO-20-017 | 2020-01-30 | CAPEX 2020 Transmission & Dist. Lines Realignment of Pipelines Affected by DPWH Projects | Prop. 150mm Pipeline Realignment | Brgy. Tablon |  |  | 12 wd = 81 mandays | not started | [14 empty] | recvd 1/30/2020
|  | 56515 | 21873 | 963 | 522 | 3734 | 6580 |  | 4378 | 16177 | 94565 | 20-007-D | 2020-01-28 | IO-20-019 | 2020-01-30 | CAPEX (Other Engineering Project) | Prop. Restoration of Concrete Pavement | Phase 2 Sta. Cecilia Subd., JR Borja Extrn., Camaman-an | 2020-02-10 | 2020-03-23 | 5 wd = 31 mandays | completed | [13 empty] | 100% | recvd 2/3/2020
|  | 311452.9 | 96779.3 |  |  | 4495.4 | 17550 |  | 38115.04 | 60160.44 | 468392.64 | 20-008-A | 2020-01-29 | IO-20-2020 | 2020-02-05 | CAPEX 2020 (Transmission & Dist. Mains, Various Sizes) | Prop. 100mm UPVC Pipeline Extension with 3 units 50mm Water Meter Stub-out | Caballero & Daing Compound, Zone 7 Bulua |  |  | 19 wd = 138 mandays | not started | [14 empty] | 2020-02-06
|  | 298940.5 | 138768 |  | 1182 | 13972 | 8305 |  | 29314 | 52773 | 490481.5 | 20-009-F | 2020-02-05 | IO-20-021 | 2020-02-10 | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 75mm Pipeline Extension with 4 units 50mm Water Meter Stub-out | Zone 3 Barra Opol |  |  | 40 wd = 234 mandays | not started | [14 empty] | 2020-02-11
[10 empty] | 4601090.25 | 4601090.25 | 20-010 |  |  |  | CAPEX-6M | Prop. Water Supply System | Berjaya, Bugo CDO | 2020-06-29 |  | 127 cd | in progress | [13 empty] | 90% |  | NTP June 26, 2020
|  | 102647 | 45409 |  |  | 8293 | 13780 |  | 5147 | 27220 | 175276 | 20-012-A | 2020-02-06 | IO-20-023 | 2020-02-10 | CAPEX 2020 (Other Engineering Project) | Prop. Installation of Data Logger on COBI Pipeline Stub-out | South Diversion Road |  |  | 8 cd = 72 mandays | not started | [14 empty] | 2020-02-17
|  | 20182 | 22445 |  | 252 | 3276 | 14188 |  | 3137 | 20853 | 63480 | 20-014-D | 2020-02-24 |  |  | CAPEX 2020 (Other Engineering Project) | Prop. Temporary Fence | PW 31, Ayesa subd. Camaman-an |  |  | 15 wd | not started | [14 empty] | 2020-02-24
|  | 195647 | 132170 |  | 253 | 19990 | 33303 |  | 59394 | 112940 | 440757 | 20-013-A | 2020-03-15 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 300mm Pipeline Realignment | Macanhan, Carmen | 2020-02-28 |  |  | in progress | [13 empty] | 90% |  | remaining works - restoration
|  | 933236 | 386710 |  | 252 | 58474 | 145653 |  | 150400 | 354779 | 1674725 | 20-016-A | 2020-05-16 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 300mm Temporary Pipeline Realignment | Bigaan Bridge Gusa, CDOC | 2020-03-04 | 2020-09-14 |  | completed | [13 empty] | 100% |  | stopped 3/6/20, resume work 5/20/20
|  | 166441 | 63958 |  |  | 9157 | 17020 |  | 34334 | 60511 | 290910 | 20-017 | 2020-07-10 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 100mm Distribution Line & Transfer of Existing 75mm BOV | Zone 8 Cugman, CDO | 2020-02-21 | 2020-06-08 |  | completed | [13 empty] | 100% |  | for turn over
[12 empty] | 20-018-D | 2020-03-16 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. Installation of 1 unit MSO | Tablon Evacuation Center |  |  |  | cancelled | [15 empty] | for cancellation, same tapping with existing MSO
|  | 22206.74 | 5193 |  | 865 |  | 1513 |  | 20256 | 22634 | 50033.74 | 20-019-A | 2020-03-16 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 300mm Steel Pipe Realignment | Brgy. 24 Osmena St. CDO |  |  | 2 cd | not started | [14 empty] | 2020-04-13
|  | 124095.75 | 73876 |  |  |  | 11250 |  | 6943 | 18193 | 216164.75 | 20-021-D | 2020-03-16 |  |  | CAPEX 2020 (Other Engineering Project) | Prop. Rehabilitation of 600mm Electromagnetic Flow Meter Manhole Cover | Take off point Lumbia |  |  | 19 wd | not started | [14 empty] | 2020-04-13
|  | 20943.74 | 5193 |  | 865 |  | 1613 |  | 20256 | 22734 | 48870.74 | Com2020-021-F | 2020-03-31 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 1 unit Public MSO | Z-10, Bulua |  |  | 2 wd | not started | [14 empty] | 2020-05-07
|  | 15783 | 4161 |  | 249 |  | 962.5 |  | 2083 | 3294.5 | 23238.5 | Com 2020-022-F | 2020-04-02 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 1 unit Public MSO | Z-4 Basak Pasil Kauswagan |  |  | 2 wd | not started | [14 empty] | 2020-04-30
|  | 22438 | 8048 |  |  | 86 |  |  | 22918 | 23004 | 53490 | Com 2020-023-F | 2020-04-02 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 1 unit Public MSO | Z-2, Bulua CDO |  |  | 4 wd | not started | [14 empty] | 2020-04-30
|  | 62442.81 | 14721 |  | 1590 |  | 2090 |  | 4792 | 8472 | 85635.81 | 20-023-F | 2020-03-27 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 75mm Distribution Line w/ 1 unit MSO | Zone 13, Puli Upper Carmen |  |  | 5 wd | not started
|  | 674851 | 79957 |  | 12319 |  | 10250 |  | 53209 | 75778 | 830586 | 20-024-F | 2020-03-31 |  |  | CAPEX2020, VEI WP4 | Prop. 31 units 50mm MSO | Pahiron Relocation Site |  |  | 23 wd = 110 mandays | not started | [14 empty] | 2020-04-13
|  | 17031.74 | 5193 |  | 865 |  | 1513 |  | 20256 | 22634 | 44858.74 | Com2020-024-F | 2020-04-21 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 1 unit 50mm MSO | Zone 1, Lower Bulua |  |  | 2 wd | not started | [14 empty] | 2020-05-07
|  | 42404 | 21873 | 963 | 522 | 3734 | 6580 |  | 3531 | 15330 | 79607 | 20-025-D | 4/220/20 |  |  | Capex 2020, Other Eng'g. Projects | Prop. Restoration of Concrete Pavement | Poblacion Opol - near Titing's kitchenette |  |  | 5 wd | not started | [14 empty] | 2020-06-01
|  | 49799.3 | 21873 | 963 | 522 | 3734 | 6580 |  | 3975 | 15774 | 87446.3 | 20-026-D | 2020-04-20 |  |  | Capex 2020, Other Eng'g. Projects | Prop. Restoration of Concrete Pavement | Saarenas Rd. Bulua |  |  | 5 wd | not started | [14 empty] | 2020-05-07
|  | 42404 | 21873 | 963 | 522 | 3734 | 6580 |  | 3531 | 15330 | 79607 | 20-027-D | 2020-04-20 |  |  | Capex 2020, Other Eng'g. Projects | Prop. Restoration of Concrete Pavement | Opol Highway - (near entrance Roan) |  |  | 5 wd | not started | [14 empty] | 2020-06-02
|  | 101748.4 | 41155 |  |  | 6147 | 5200 |  | 19113 | 30460 | 173363.4 | 20-028-F | 2020-04-20 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 50mm Service Line w/ 2 unit MSO | camaman-an, CDO |  |  | 15 WD | not started | [14 empty] | 2020-05-07
|  | 354887 | 238202 | 1486 | 1106 | 46383 | 44095 |  | 42193 | 135263 | 728352 | 20-031-F | 2020-06-03 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 500mm & 300mm Pipeline Realignment | Ayesa | 2020-05-04 | 2020-08-14 | 40 wd | completed | [13 empty] | 100% |  | schedule for interconnection on July 9 for 300mm Steel pipeline.
|  | 2385057 | 233432 | 963 | 296 | 39716 | 46020 |  | 185857 | 272852 | 2891341 | 20-033-A | 2020-05-05 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. Realignment of 600mm Steel Pipelines | JR Borja Extn. |  |  | 45 cd | not started | [14 empty] | 2020-06-01
|  | 132019 | 44385 |  | 8930 |  | 21450 |  | 9458 | 39838 | 216242 | 20-037-A | 2020-05-15 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 150mm UPVC Pipeline Interconnection | Buena Oro Macasandig | May 30,2020 | 2020-06-02 | 7 cd | Completed | [13 empty] | 100% | 2020-05-19
|  | 15528 | 4024 |  |  | 68 |  |  | 1908 | 1976 | 21528 | Com2020-25-F | 2020-05-12 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 1 unit Public MSO | Zone 1, Igpit Opol | 2020-09-05 | 2020-09-05 | 2 days | completed | [14 empty] | June 3, 2020
|  | 43107 | 33285 |  |  | 1642 |  |  | 25398 | 27040 | 103432 | Com2020-26-F | 2020-05-27 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 1 unit Public MSO | Bonbon, CDO |  |  | 12 wd | not started | [14 empty] | June 29, 2020
|  | 40290 | 23366 | 3694 |  |  | 1513 |  | 21756 | 26963 | 90619 | Com 2020-27-F | 2020-05-27 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 1 unit Public MSO | Zone 1, Bulua, CDO |  |  | 9 wd | not started | [14 empty] | June 29, 2021
|  | 352335.5 | 92210 |  |  | 18173 | 30480 |  | 20469 | 69122 | 513667.5 | 20-038-F | 2020-06-19 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Prop. 150mm UPVC Pipeline Etension & Interconnection | Buena Oro Macasandig | 2020-06-16 |  | 15 wd | Completed | [13 empty] | 100%
|  | 41351 | 25461.41 |  | 1304.66 |  |  |  | 5007.12 | 6311.78 | 73124.19 | Com 2020-028-F | 2020-07-06 |  |  | Capex MO 2020 | Prop. 1 unit Public MSO | Zone 3, Barra Opol |  |  | 9 wd | not started | [14 empty] | July 7, date recvd.
[12 empty] | 20-039-A |  |  |  | Capex 2020 | Prop. Restoration of Conc. Pavement | Concordio Diel, Zayas Carmen | 2020-07-20 | 2020-08-07 |  | Completed | [13 empty] | 100%
|  | 329921 | 82329 | 1486 | 1106 | 15981 | 13900 |  | 35077 | 67550 | 479800 | 20-041-D | 2020-07-15 |  |  | CAPEX 2020 | Prop. Installation of Railings (3rd flr) and partitons for 2nd & 3rd flr. CR | Tin-ao, Sub-office Bldng. |  |  |  | not started | [14 empty] | 2020-06-20
|  | 56682 | 11819.28 |  | 635.15 |  |  |  | 6846.84 | 7481.99 | 75983.27 | Com2020-29-F | 2020-07-15 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Proposed 3 units 50mm Public MSO | Zone 8, Cugman |  |  | 4 days = 20 mandays | Completed | [13 empty] | 100%
|  | 16004.74 | 4208 |  |  | 689 | 963 |  | 20228 | 21880 | 42092.74 | Com2020-30 | 2020-08-05 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Proposed 1 unit 50mm Public MSO | Mahayah Lumbia |  |  | 3 days | [15 empty] | 2020-08-11
|  | 49542 | 8861.46 |  |  | 489.48 | 825 |  | 6113.79 | 7428.27 | 65831.73 | Com2020-31 | 2020-07-28 |  |  | CAPEX 2020 Transmission & Dist. Mains, Various Sizes) | Proposed 3 unit 50mm Public MSO | Lumbia | 2020-09-05 | 2020-09-05 | 3 days | Completed | [13 empty] | 100%
|  | 38544 | 23165 |  |  | 1158 |  |  | 4670 | 5828 | 67537 | Com 2020-37-F | 2020-08-27 |  |  | Capex 2020 | Proposed 1 unit 50mm Public MSO | Reyes Cpd. Dist. 5, P-10, Canitoan |  |  | 8 wd | not started | [14 empty] | 2020-10-09
|  | 15385 | 2953.82 |  |  | 198.16 |  |  | 1891.2 | 2089.36 | 20428.18 | Com 2020-39F | 2020-08-16 |  |  | Capex 2020 | Proposed 1 unit 50mm Public MSO | Z-1, Delima St. Lumbia |  |  | 3wd | not started | [14 empty] | 2020-10-09
|  | 411197 | 171580 |  |  | 14547 | 24295 |  | 42898 | 81740 | 664517 | 20-042-A | 2020-08-05 |  |  | capex 2020 | Prop. 100mm & 75mmPipeline Extension w/ 2 units MSO | Zone 7, Bulua |  |  | 30 wd | [15 empty] | 2020-08-11
|  | 121253 | 92048 |  | 252 | 14146 | 25998 |  | 50859 | 91255 | 304556 | 20-043-A | 2020-08-04 |  |  | capex 2020 | Prop. 200mm Realignment | Gaabucayan St., Agora | 2020-08-10 | 2020-08-27 | 15 wd | Completed | [13 empty] | 100%
|  | 115133.1 | 34428 | 732 | 408 | 6022 | 7750 |  | 14676 | 29588 | 179149.1 | 20-045-A | 2020-08-07 |  |  | capex 2020 | Prop. 150mm Commercial Fire Hydrant | Capt. Vicente Roa St. |  |  | 10 wd
|  | 346224.5 | 150187 |  | 1182 | 15664 | 26070 |  | 63834 | 106750 | 603161.5 | 20-046-A | 2020-08-07 |  |  | capex 2020 | Prop. 75mm Pipeline extension w/ 2 units 50mm MSO | Across CEO, Kauswagan |  |  | 41 wd
|  | 61173 | 19308 |  | 1182 | 1573 | 2915 |  | 5288 | 10958 | 91439 | com2020-047-F | 2020-08-12 |  |  | capex 2020 | Prop. 50mm MSO | F. Delima St. Lumbia | 2020-09-12 | 2020-09-12 | 1 wd | Completed | [13 empty] | 100%
|  | 306247 | 54070.25 | 963.25 | 346.25 | 8485 | 15375 |  | 20682.08 | 45851.58 | 406168.83 | 20-048-D | 2020-08-17 |  |  | capex 2020 | Prop. Steel Formworks & Scaffoldings (for civil work projects) | COWD Shop, Kauswagan |  |  | 10 wd | not started
|  | 18484 | 5907.64 |  | 343.82 |  |  |  | 2263.08 | 2606.9 | 26998.54 | Com2020-32-F | 2020-08-03 |  |  | capex 2020 | Prop. 1 unit Public MSO | Zone 10, Impantao, Bulua |  |  | 2 wd | not started
|  | 42393 | 26584.38 |  | 1363.46 |  |  |  | 5132.16 | 6495.62 | 75473 | Com2020-33-F | 2020-08-17 |  |  | capex 2020 | Prop. 1 unit Public MSO | Z-8, Garcia Cpd. Bulua |  |  | 9 wd | not started
|  | 41846 | 26584.38 |  | 1363.45 |  | 1925 |  | 5355.27 | 8643.72 | 77074.1 | Com2020-35-F | 2020-08-17 |  |  | capex 2020 | Prop. 1 unit Public MSO | Z-7A, Igpit Opol |  |  | 9 wd | not started
|  | 44269 | 26584.38 |  | 1363.45 |  |  |  | 5357.28 | 6720.73 | 77574.11 | Com2020-36-F | 2020-08-17 |  |  | capex 2020 | Prop. 1 unit Public MSO | Zone 5, Camansi Iponan |  |  | 9 wd | not started
[10 empty] | 6252980.22 | 6252980.22 | 19-037-D | 2020-08-25 |  |  |  | Prop. Elevated Generator stl. Platform | MBSP | 2020-09-04 |  | 180 wd | in-progress
|  | 16771 | 4430 |  | 270.9 |  |  |  | 2057.52 | 2328.42 | 23529.42 | Com2020-034-F | 2020-08-25 |  |  | CAPEX 2020 | Prop. 1 unit Public MSO | Purok 7 Seaside Gusa |  |  |  | not started
|  | 678413 | 73207 |  |  | 7098 | 10325 |  | 24657 | 42080 | 793700 | 20-049 F | 2020-09-04 |  |  | Disaster Risk Fund | Prop. 50mm Service line w/ 4 units MSO | Malasag Cugman | 2020-09-08 |  |  | in-progress
|  | 16467.24 | 5611 |  | 918 |  | 963 |  | 20288 | 22169 | 44247.24 | Com2020-040-F | 2020-09-02 |  |  | Capex 2020 | Prop. 1 unit Public MSO | Z-9, Bulua |  |  |  | not started | [14 empty] | 2020-09-15
|  | 71824 | 22638 |  | 3850 |  | 4500 |  | 2112 | 10462 | 104924 | 20-051-F | 2020-09-07 |  |  | Capex 2020 | Prop. 1 unit Public MSO | Basak Drive Z-4, Pasil Kauswagan |  |  |  | not started | [14 empty] | 2020-09-15
|  | 18602 | 4430 |  | 270 |  | 412.5 |  | 2339.12 | 3021.62 | 26053.62 | Com2020-41-F | 2020-09-07 |  |  | Capex 2020 | Prop. 1 unit Public MSO | Ysalina St. Lumbia | [18 empty] | 2020-09-22
|  | 304085 | 115060 |  | 1182 | 10298 | 10725 |  | 9211 | 31416 | 450561 | 20-052-F | 2020-10-30 |  |  | Capex 2020 | Prop. 3 units Public MSO | Apovel subd. Bulua |  |  |  | in-progress
|  | 57000 | 24560 |  |  | 3565 | 4000 |  | 2025 | 9590 | 91150 | 20-053-F | 2020-09-25 |  |  | Capex 2020 | Prop. Transfer of 50mm MSO | Pagatpat Ressetlement Area P-2 Pamalihi, Pagatpat |  |  |  | not started | [14 empty] | 2020-09-30
|  | 38582.74 | 22445 |  |  | 3674 | 10725 |  | 20716 | 35115 | 96142.74 | Com2020-42-F | 2020-09-21 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Sambag, Bugo |  |  | 8 wd | not started | [14 empty] | 2020-10-05
|  | 49061 | 38399.66 |  |  | 1946 | 5775 |  | 26978.57 | 34699.57 | 122160.23 | Com2020-043-F | 2020-10-01 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 8, Bugo |  |  | 13 wd | not started | [14 empty] | 2020-10-05
|  | 119626 | 23639.56 |  |  | 1217.79 | 2475 |  | 14771 | 18463.79 | 161729.35 | Com2020-044-F | 2020-09-21 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Ysalina St. Lumbia |  |  | 8 wd | not started | [14 empty] | 2020-10-08
|  | 47072 | 8861.46 |  |  | 480.48 | 5775 |  | 6559.89 | 12815.37 | 68748.83 | Com2020-045-F | 2020-10-06 |  |  | Capex 2020 | Prop. 2 units 50mm Public MSO | Upper Apovel, Bulua, CDO | 2020-09-26 | 2020-10-03 | 1 wd | completed | [13 empty] | 100% | 2020-10-08
|  | 23157.74 | 5611 |  |  | 918 | 1513 |  | 20256 | 22687 | 51455.74 | Com2020-046-F | 2020-10-06 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Z-9, Anhawon, Bulua |  |  | 2 wd | not started | [14 empty] | 2020-10-08
|  | 272911 | 240508 |  | 252 | 36622 | 81363 |  | 87013 | 205250 | 718669 | 20-055-A | 2020-10-05 |  |  | Capex 2020 | Prop. 300mm and 100mm Pipeline Realignment | CM Recto Ave., Lapasan |  |  | 35 wd | not started | [14 empty] | 2020-10-09
[10 empty] | 0 | 4218953 | 17-010-D PR#19-06-07-0061 | 2017-02-21 |  |  | Capex 2020 | Prop. Expansion of Level 3 WSS forCDORSHP-1 | Phase 3, CDORSHP-1, Talongan Relocation Site, Calaanan
|  | 87922 | 55818.2 |  | 1606.62 |  | 1587.5 |  | 10833.77 | 14027.89 | 157768.09 | Com 2020-048 | 2020-10-19 |  |  | Capex 2020 | Prop. 1 unit Public MSO | Zone 1 Delima St. Lumbia |  |  |  | not started | [14 empty] | 2020-10-24
|  | 67449.3 | 21873 |  | 963 | 3772 | 7100 |  | 6437 | 18272 | 107594.3 | 20-063 | 2020-10-16 |  |  | Capex 2020 | Prop. 75mm BLOW off valve | Capt. V. Roa St. |  |  | 10 wd | not started
|  | 46043 | 21873 | 963 | 563 | 3734 | 6580 |  | 3750 | 15590 | 83506 | 20-062 | 2020-10-15 |  |  | Capex 2020 | Prop. Restoration of Conc. Pavement | P-2, Sta Cecilia subd. Gusa |  |  |  | not started
|  | 36143 | 35445.84 |  | 1800.44 |  | 13137.5 |  | 26532.79 | 41470.73 | 113059.57 | Com 2020-049-F | 2020-10-20 |  |  | Capex 2020 | Prop. 1 unit 50mm MSO | Zone 4, Mahogany Tablon |  |  |  | not started | [14 empty] | 2020-11-04
|  | 37010 | 4826.73 |  | 277.59 |  | 1587.5 |  | 4724.33 | 6589.42 | 48426.15 | Com 2020-050-F | 2020-10-20 |  |  | Capex 2020 | Prop. 1 unit 50mm MSO | Zone 2, Sabalo Lumbia |  |  |  | not started | [14 empty] | 2020-11-04
|  | 18802.25 | 4826.73 |  |  | 277.59 | 1587.5 |  | 2539.4 | 4404.49 | 28033.47 | Com2020-051-F | 2020-10-30 |  |  | Capex 2020 | Prop. 1 unit 50mm MSO | Zone 8, Lower Bulua |  |  |  | not started | [14 empty] | 2020-11-04
|  | 393508 | 253477 |  | 252 | 38827 | 63513 |  | 92056 | 194648 | 841633 | 20-061-A | 2020-11-18 |  |  | Capex 2020 | Prop. 600mm & 400mm Steel Pipeline realignment | Camaman-an Road along Hayes st. ,CDO |  |  |  | not started | [14 empty] | 2020-11-23
|  | 64448.48 | 11223 |  |  | 1837 | 3943 |  | 20377 | 26157 | 101828.48 | COM2020-052-F | Oct. 27, 2020 |  |  | Capex 2020 | Prop. 4 units MSO | Zone 7, Agusan, CDO |  |  |  | not started | [14 empty] | 2020-11-25
|  | 40623.74 | 25251 |  |  | 4133 | 3209 |  | 20340 | 27682 | 93556.74 | COM2020-053-F | 2020-10-27 |  |  | capex 2020 | Prop. 1 unit MSO | Zone 4, Sarat Agusan |  |  |  | not started | [14 empty] | 2020-11-25
|  | 48190.74 | 44890 |  |  | 7347 | 10909 |  | 56770 | 75026 | 168106.74 | COM2020-054-F | 2020-11-04 |  |  | capex 2020 | Prop. 1 unit MSO | Z-1, Sofia Cpd. Bulua
|  | 201004 | 92095 |  | 1407 | 10114 | 2120 |  | 13623 | 27264 | 320363 | 20-066-A | 2010-10-30 |  |  | Capex 2020 | Prop. 75mm Pipeline Extension w/ 1 unit MSO | Zone 10, Bulua |  |  | 21 wd | not started | [14 empty] | 2020-11-26
|  | 59999 | 34749 |  |  | 4788 | 3300 |  | 9489 | 17577 | 112325 | 20-067-A | 2020-11-20 |  |  | Capex 2020 | Prop. 75mm w/ 1 unit MSO | Zone 7, Bulua |  |  |  | not started | [14 empty] | 2020-11-25
|  | 191656.25 | 76933 |  |  | 14075 | 12563 |  | 7635 | 34273 | 302862.25 | 20-068-A | 2020-10-30 |  |  | Capex 2020 | Prop. 100mm UPVC Pipe By Pass Line | Silver Creek Phase 1, Canitoan |  |  | 18 wd | not started | [14 empty] | 2020-11-26
|  | 90514 | 75731 | 252 |  | 11331 | 28238 |  | 42013 | 81834 | 248079 | 20-069-A |  |  |  | Capex 2020 | Prop. 150mm Pipeline Realignment | NHA Phase 2 junction, Kauswagan |  |  | 15 wd | not started | [14 empty] | 2020-11-26
|  | 77171 | 79615 |  | 252 | 11896 | 28363 |  | 13279 | 53790 | 210576 | 20-070-D | 2020-11-09 |  |  | Capex 2020 | Prop. New Chlorine House Storage |  |  |  |  | not started | [14 empty] | 2020-11-25
|  | 2772098.93 | 238363 | 10456 | 6150 | 36676 | 87355 |  | 215989 | 356626 | 3367087.93 | 20-071-D | 2020-11-09 |  |  | CAPEX 2020 | Prop. Transfer of 350mm Electromagnetic flowmeter | Bugo, Booster |  |  |  | not started | [14 empty] | 2020-11-25
|  | 27451 | 16843 |  | 2358 |  | 2250 |  | 1427 | 6035 | 50329 | 20-073-A | 2020-11-11 |  |  | Capex 2020 | Prop. 25mm Service line Extension | Bagakay, Molave Malasag |  |  |  | not started | [14 empty] | 2020-11-25
|  | 891667 | 438935 |  | 1182 | 34089 | 43780 |  | 188199 | 267250 | 1597852 | 20-074-f | 2020-11-11 |  |  | Capex 2020 | Prop. 150mm & 100mm Pipeline Extension w/ 6 units MSO | KAHOA, Zone 4 Pasil, Kauswagan |  |  |  | not started | [14 empty] | 2020-11-23
|  | 35872 | 19306.92 |  |  | 933.07 | 2550 |  | 24912.14 | 28395.21 | 83574.13 | COM2020-055 | 2020-11-05 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Ramonal Village, Camaman-an |  |  |  | not started | [14 empty] | 1/5/2021 recvd.
|  | 30816 | 16089.1 |  |  | 767.41 | 1587.5 |  | 3981.05 | 6335.96 | 53241.06 | COM2020-056 | 2020-11-05 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 6A Cugman |  |  |  | not started | [14 empty] | 1/6/21 recvd
|  | 17706 | 3217.82 |  |  | 204.75 | 1587.5 |  | 2407.85 | 4200.1 | 25123.92 | Com2020-57-F | 2020-11-04 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 9, Cugman |  |  | 1 wd | not started | [14 empty] | 2020-12-01
|  | 44555.74 | 39375 |  |  | 6458 | 10909 |  | 20725 | 38092 | 122022.74 | COM2020-058 | 2020-11-09 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 6, Tinago Kauswagan |  |  |  | not started | [14 empty] | 2021-01-05
|  | 18014 | 3108.45 |  |  | 199.29 |  |  | 1846.4 | 2045.69 | 23168.14 | COM2020-059 | 2020-12-11 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Samar St. Aluba, Macasandig |  |  |  | not started | [14 empty] | 1/5/21 recvd.
|  | 16332.74 | 3938 |  |  | 646 | 1697 |  | 85 | 2428 | 22698.74 | COM2020-060 | 2020-11-12 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 2. Kauswagan |  |  |  | not started | [14 empty] | 1/5/21 recvd.
|  | 21497 | 6435.54 |  | 350.42 |  | 2550 |  | 23187.14 | 26087.56 | 54020.1 | COM2020-061 | 2020-11-23 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | 31st st. Nazareth, CDO |  |  | 2 wd | not started | [14 empty] | 2021-01-14
|  | 17727 | 4826.73 |  | 277 |  | 1100 |  | 22517.24 | 23894.24 | 46447.97 | COM2020-062 | 2020-11-27 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Z-6 Capisnon Kaus |  |  | 2 wd | not started | [14 empty] | 2021-01-14
|  | 26411 | 22524.74 |  | 1078.73 |  | 1587.5 |  | 3452.45 | 6118.68 | 55054.42 | COM2020-063 | 2020-11-27 |  |  | capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 2 Kalye Pogi, Cugman |  |  | 1wd | not started | [14 empty] | 2021-01-08
|  | 17357 | 4826.73 |  | 277.59 |  | 137.5 |  | 2148.47 | 2563.56 | 24747.29 | COM2020-064 | 2020-11-27 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Purok 6, Urban Poor Asso., Gusa |  |  | 2 wd | not started | [14 empty] | 2021-01-11
|  | 17357 | 4826.73 |  | 277.59 |  | 137.5 |  | 2148.47 | 2563.56 | 24747.29 | COM2020-066 | 2020-11-27 |  |  | capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 1 Igpit Opol |  |  | 2 wd | not started | [14 empty] | 2021-01-14
|  | 34684 | 19306.92 |  | 933.07 |  | 1725 |  | 24645.83 | 27303.9 | 81294.82 | COM2020-067 | 2020-12-02 |  |  | Capex 2020 | Prop. 1 unit 50mm Public MSO | Zone 4, Bugo |  |  | 6 wd | not started | [14 empty] | 2021-01-14
|  | 476629 | 128564 | 4183 | 9840 | 20321 | 42200 |  | 34661 | 111205 | 716398 | 20-075-F | 2020-11-18 |  |  | Capex 2020 | Prop. Replacement of Existing Big Mechanical Meters with 50mmØ Electromagnetic Flowmeters | Limketkai Center |  |  | 26 wd | not started | [14 empty] | 2020-12-01
|  | 282429 | 93013 |  |  | 13957 | 13570 |  | 14226 | 41753 | 417195 | 20-079-A | 2020-11-26 |  |  | Capex 2020 | Prop. 75mm Distribution Line w/ 5 MSO | Buara Bayabas |  |  | 31 wd | not started | [14 empty] | 2020-12-14
|  | 200998.2 | 82375 |  |  | 10504 | 14625 |  | 27309 | 52438 | 335811.2 | 20-080-! | 2020-12-02 |  |  | Capex 2020 | Prop. 75mm Pipeline Extension w/ 2 units MSO | Tina-ao, Agusan |  |  |  | not started | [14 empty] | 2021-01-06
[10 empty] | 0 | 1063244.93 | 20-085 | 2020-12-29 |  |  | Capex 2020 | Prop. Rehabilitation of Roofing & Ceiling | COWD Shop Kaus, CDO |  |  |  | contract out
[10 empty] | 0 | 2139231 | 20-086 | 2020-12-29 |  |  | Capex 2020 | Prop. Cement Go Down Storage | COWD Shop Kaus, CDO |  |  |  | contract out
|  | 2395 | 50233 |  |  | 10044 | 7800 |  | 1755 | 19599 | 72227 | 20-087 | 2020-12-29 |  |  | paid by applicant O.R. #4301825 | Prop. Pipeline Interconnection & 1 unit 75mm Meter Assy. w/ chamber | Corrales Extn. Beside Capitol University. CEBU LAND MASTER

## Sheet4
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS
|  | NO. | DATE
1 | 577789.39 | 20-001-A | 2020-01-13 | Prop. Extension of 100mm Distribution Line, 200mm Distribution Line w/ 75mm Blow Off Valve | Luminarias St., JR Borja Extn. | not started
2 | 3145906.94 | 20-002-A | 2020-01-13 | Prop. 100mm Pipeline Extension with 14 Units 50mm MSO & DMA | Sitio Tierra Del Puerto, Camaman-an | not started
3 | 23896.65 | Com2020-003-F | 2020-01-21 | Prop. 1-Unit 50mmØ Public Stub-out | Sambaan Village, Patag | completed
4 | 1148773.72 | 20-003-A | 2020-01-15 | Prop. Rehabilitation of Water Supply System | Macapaya Phase 1A, Camaman-an | in progress
5 | 66543.48 | Com2020-004-F | 2020-01-21 | Prop. 1-Unit 50mmØ Public Stub-out | Brgy. 9, Pabayo St. | not started
6 | 66028.24 | Com2020-004-F | 2020-02-05 | Prop. 1-Unit 50mmØ Public Stub-out | JR Borja Extension, Gusa | not started
7 | 4487536.04 | 20-004-A | 2020-01-17 | Prop. 200mm Pipeline Extension | Mahogany to Pamalihi Relocation Site | not started
8 | 132457 | Com2020-005-F | 2020-02-05 | Prop. 1-Unit 50mmØ Public Stub-out | Amfana St., Carmen | not started
9 | 550297 | 20-005-F | 2020-01-22 | Prop. 400mm Pipe Realignment | J Seriña St., Carmen | not started
10 | 94823.42 | Com2020-006-F | 2020-02-05 | Prop. 1 Unit 50mm Public Stub-out | B3 L2 Ficcoville, Iponan | not started
11 | 113269.05 | Com2020-007-F | 2020-02-14 | Prop. 1 Unit 50mm Public Stub-out | San Isidro Lumbia | completed
12 | 94716.19 | Com2020-009-F | 2020-03-02 | Prop. 1 Unit 50mm Public Stub-out | Zone 1 Igpit Opol | not started
13 | 81100.37 | Com2020-10-F | 2020-02-21 | Prop. 2 Unit 50mm Public Stub-out | Tierra de Puerto, Camaman-an, CDO | not started
14 | 77188.57 | Com2020-011-F | 2020-03-02 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia | not started
15 | 46501.76 | Com2020-012-F | 2020-02-24 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia | completed
16 | 57840 | Com2020-013-F | 2020-03-05 | Prop. 1 Unit 50mm Public Stub-out | Zone 6, Gawad Kalinga Bugo | completed
17 | 222459 | 20-006-A | 2020-01-23 | Prop. 150mm Pipeline Realignment | Brgy. Tablon | not started
18 | 94565 | 20-007-D | 2020-01-28 | Prop. Restoration of Concrete Pavement | Phase 2 Sta. Cecilia Subd., JR Borja Extrn., Camaman-an | completed
19 | 468392.64 | 20-008-A | 2020-01-29 | Prop. 100mm UPVC Pipeline Extension with 3 units 50mm Water Meter Stub-out | Caballero & Daing Compound, Zone 7 Bulua | not started
20 | 490481.5 | 20-009-F | 2020-02-05 | Prop. 75mm Pipeline Extension with 4 units 50mm Water Meter Stub-out | Zone 3 Barra Opol | not started
21 | 4601090.25 | 20-010 |  | Prop. Water Supply System | Berjaya, Bugo CDO | in progress
22 | 175276 | 20-012-A | 2020-02-06 | Prop. Installation of Data Logger on COBI Pipeline Stub-out | South Diversion Road | not started
23 | 63480 | 20-014-D | 2020-02-24 | Prop. Temporary Fence | PW 31, Ayesa subd. Camaman-an | not started
24 | 440757 | 20-013-A | 2020-03-15 | Prop. 300mm Pipeline Realignment | Macanhan, Carmen | in progress
25 | 1674725 | 20-016-A | 2020-05-16 | Prop. 300mm Temporary Pipeline Realignment | Bigaan Bridge Gusa, CDOC | completed
26 | 290910 | 20-017 | 2020-07-10 | Prop. 100mm Distribution Line & Transfer of Existing 75mm BOV | Zone 8 Cugman, CDO | completed
27 |  | 20-018-D | 2020-03-16 | Prop. Installation of 1 unit MSO | Tablon Evacuation Center | cancelled
28 | 50033.74 | 20-019-A | 2020-03-16 | Prop. 300mm Steel Pipe Realignment | Brgy. 24 Osmena St. CDO | not started
29 | 216164.75 | 20-021-D | 2020-03-16 | Prop. Rehabilitation of 600mm Electromagnetic Flow Meter Manhole Cover | Take off point Lumbia | not started
30 | 48870.74 | Com2020-021-F | 2020-03-31 | Prop. 1 unit Public MSO | Z-10, Bulua | not started
31 | 23238.5 | Com 2020-022-F | 2020-04-02 | Prop. 1 unit Public MSO | Z-4 Basak Pasil Kauswagan | not started
32 | 53490 | Com 2020-023-F | 2020-04-02 | Prop. 1 unit Public MSO | Z-2, Bulua CDO | not started
33 | 85635.81 | 20-023-F | 2020-03-27 | Prop. 75mm Distribution Line w/ 1 unit MSO | Zone 13, Puli Upper Carmen | not started
34 | 830586 | 20-024-F | 2020-03-31 | Prop. 31 units 50mm MSO | Pahiron Relocation Site | not started
35 | 44858.74 | Com2020-024-F | 2020-04-21 | Prop. 1 unit 50mm MSO | Zone 1, Lower Bulua | not started
36 | 79607 | 20-025-D | 4/220/20 | Prop. Restoration of Concrete Pavement | Poblacion Opol - near Titing's kitchenette | not started
37 | 87446.3 | 20-026-D | 2020-04-20 | Prop. Restoration of Concrete Pavement | Saarenas Rd. Bulua | not started
38 | 79607 | 20-027-D | 2020-04-20 | Prop. Restoration of Concrete Pavement | Opol Highway - (near entrance Roan) | not started
39 | 173363.4 | 20-028-F | 2020-04-20 | Prop. 50mm Service Line w/ 2 unit MSO | camaman-an, CDO | not started
40 | 728352 | 20-031-F | 2020-06-03 | Prop. 500mm & 300mm Pipeline Realignment | Ayesa | completed
41 | 2891341 | 20-033-A | 2020-05-05 | Prop. Realignment of 600mm Steel Pipelines | JR Borja Extn. | not started
42 | 216242 | 20-037-A | 2020-05-15 | Prop. 150mm UPVC Pipeline Interconnection | Buena Oro Macasandig | Completed
43 | 21528 | Com2020-25-F | 2020-05-12 | Prop. 1 unit Public MSO | Zone 1, Igpit Opol | completed
44 | 103432 | Com2020-26-F | 2020-05-27 | Prop. 1 unit Public MSO | Bonbon, CDO | not started
45 | 90619 | Com 2020-27-F | 2020-05-27 | Prop. 1 unit Public MSO | Zone 1, Bulua, CDO | not started
46 | 513667.5 | 20-038-F | 2020-06-19 | Prop. 150mm UPVC Pipeline Etension & Interconnection | Buena Oro Macasandig | Completed
47 | 73124.19 | Com 2020-028-F | 2020-07-06 | Prop. 1 unit Public MSO | Zone 3, Barra Opol | not started
48 |  | 20-039-A |  | Prop. Restoration of Conc. Pavement | Concordio Diel, Zayas Carmen | Completed
49 | 479800 | 20-041-D | 2020-07-15 | Prop. Installation of Railings (3rd flr) and partitons for 2nd & 3rd flr. CR | Tin-ao, Sub-office Bldng. | not started
50 | 75983.27 | Com2020-29-F | 2020-07-15 | Proposed 3 units 50mm Public MSO | Zone 8, Cugman | Completed
51 | 42092.74 | Com2020-30 | 2020-08-05 | Proposed 1 unit 50mm Public MSO | Mahayah Lumbia
52 | 65831.73 | Com2020-31 | 2020-07-28 | Proposed 3 unit 50mm Public MSO | Lumbia | Completed
53 | 67537 | Com 2020-37-F | 2020-08-27 | Proposed 1 unit 50mm Public MSO | Reyes Cpd. Dist. 5, P-10, Canitoan | not started
54 | 20428.18 | Com 2020-39F | 2020-08-16 | Proposed 1 unit 50mm Public MSO | Z-1, Delima St. Lumbia | not started
55 | 664517 | 20-042-A | 2020-08-05 | Prop. 100mm & 75mmPipeline Extension w/ 2 units MSO | Zone 7, Bulua
56 | 304556 | 20-043-A | 2020-08-04 | Prop. 200mm Realignment | Gaabucayan St., Agora | Completed
57 | 179149.1 | 20-045-A | 2020-08-07 | Prop. 150mm Commercial Fire Hydrant | Capt. Vicente Roa St.
58 | 603161.5 | 20-046-A | 2020-08-07 | Prop. 75mm Pipeline extension w/ 2 units 50mm MSO | Across CEO, Kauswagan
59 | 91439 | com2020-047-F | 2020-08-12 | Prop. 50mm MSO | F. Delima St. Lumbia | Completed
60 | 406168.83 | 20-048-D | 2020-08-17 | Prop. Steel Formworks & Scaffoldings (for civil work projects) | COWD Shop, Kauswagan | not started
61 | 26998.54 | Com2020-32-F | 2020-08-03 | Prop. 1 unit Public MSO | Zone 10, Impantao, Bulua | not started
62 | 75473 | Com2020-33-F | 2020-08-17 | Prop. 1 unit Public MSO | Z-8, Garcia Cpd. Bulua | not started
63 | 77074.1 | Com2020-35-F | 2020-08-17 | Prop. 1 unit Public MSO | Z-7A, Igpit Opol | not started
64 | 77574.11 | Com2020-36-F | 2020-08-17 | Prop. 1 unit Public MSO | Zone 5, Camansi Iponan | not started
65 | 6252980.22 | 19-037-D | 2020-08-25 | Prop. Elevated Generator stl. Platform | MBSP | in-progress
66 | 23529.42 | Com2020-034-F | 2020-08-25 | Prop. 1 unit Public MSO | Purok 7 Seaside Gusa | not started
67 | 793700 | 20-049 F | 2020-09-04 | Prop. 50mm Service line w/ 4 units MSO | Malasag Cugman | in-progress
68 | 44247.24 | Com2020-040-F | 2020-09-02 | Prop. 1 unit Public MSO | Z-9, Bulua | not started
69 | 104924 | 20-051-F | 2020-09-07 | Prop. 1 unit Public MSO | Basak Drive Z-4, Pasil Kauswagan | not started
70 | 26053.62 | Com2020-41-F | 2020-09-07 | Prop. 1 unit Public MSO | Ysalina St. Lumbia
71 | 450561 | 20-052-F | 2020-10-30 | Prop. 3 units Public MSO | Apovel subd. Bulua | in-progress
72 | 91150 | 20-053-F | 2020-09-25 | Prop. Transfer of 50mm MSO | Pagatpat Ressetlement Area P-2 Pamalihi, Pagatpat | not started
73 | 96142.74 | Com2020-42-F | 2020-09-21 | Prop. 1 unit 50mm Public MSO | Sambag, Bugo | not started
74 | 122160.23 | Com2020-043-F | 2020-10-01 | Prop. 1 unit 50mm Public MSO | Zone 8, Bugo | not started
75 | 161729.35 | Com2020-044-F | 2020-09-21 | Prop. 1 unit 50mm Public MSO | Ysalina St. Lumbia | not started
76 | 68748.83 | Com2020-045-F | 2020-10-06 | Prop. 2 units 50mm Public MSO | Upper Apovel, Bulua, CDO | completed
77 | 51455.74 | Com2020-046-F | 2020-10-06 | Prop. 1 unit 50mm Public MSO | Z-9, Anhawon, Bulua | not started
78 | 718669 | 20-055-A | 2020-10-05 | Prop. 300mm and 100mm Pipeline Realignment | CM Recto Ave., Lapasan | not started
79 | 4218953 | 17-010-D PR#19-06-07-0061 | 2017-02-21 | Prop. Expansion of Level 3 WSS forCDORSHP-1 | Phase 3, CDORSHP-1, Talongan Relocation Site, Calaanan
80 | 157768.09 | Com 2020-048 | 2020-10-19 | Prop. 1 unit Public MSO | Zone 1 Delima St. Lumbia | not started
81 | 107594.3 | 20-063 | 2020-10-16 | Prop. 75mm BLOW off valve | Capt. V. Roa St. | not started
82 | 83506 | 20-062 | 2020-10-15 | Prop. Restoration of Conc. Pavement | P-2, Sta Cecilia subd. Gusa | not started
83 | 113059.57 | Com 2020-049-F | 2020-10-20 | Prop. 1 unit 50mm MSO | Zone 4, Mahogany Tablon | not started
84 | 48426.15 | Com 2020-050-F | 2020-10-20 | Prop. 1 unit 50mm MSO | Zone 2, Sabalo Lumbia | not started
85 | 28033.47 | Com2020-051-F | 2020-10-30 | Prop. 1 unit 50mm MSO | Zone 8, Lower Bulua | not started
86 | 841633 | 20-061-A | 2020-11-18 | Prop. 600mm & 400mm Steel Pipeline realignment | Camaman-an Road along Hayes st. ,CDO | not started
87
88 | 101828.48 | COM2020-052-F | Oct. 27, 2020 | Prop. 4 units MSO | Zone 7, Agusan, CDO | not started
89 | 93556.74 | COM2020-053-F | 2020-10-27 | Prop. 1 unit MSO | Zone 4, Sarat Agusan | not started
90 | 168106.74 | COM2020-054-F | 2020-11-04 | Prop. 1 unit MSO | Z-1, Sofia Cpd. Bulua
91 | 320363 | 20-066-A | 2010-10-30 | Prop. 75mm Pipeline Extension w/ 1 unit MSO | Zone 10, Bulua | not started
92 | 112325 | 20-067-A | 2020-11-20 | Prop. 75mm w/ 1 unit MSO | Zone 7, Bulua | not started
93 | 302862.25 | 20-068-A | 2020-10-30 | Prop. 100mm UPVC Pipe By Pass Line | Silver Creek Phase 1, Canitoan | not started
94 | 248079 | 20-069-A |  | Prop. 150mm Pipeline Realignment | NHA Phase 2 junction, Kauswagan | not started
95 | 210576 | 20-070-D | 2020-11-09 | Prop. New Chlorine House Storage |  | not started
96 | 3367087.93 | 20-071-D | 2020-11-09 | Prop. Transfer of 350mm Electromagnetic flowmeter | Bugo, Booster | not started
97 | 50329 | 20-073-A | 2020-11-11 | Prop. 25mm Service line Extension | Bagakay, Molave Malasag | not started
98 | 1597852 | 20-074-f | 2020-11-11 | Prop. 150mm & 100mm Pipeline Extension w/ 6 units MSO | KAHOA, Zone 4 Pasil, Kauswagan | not started
99 | 83574.13 | COM2020-055 | 2020-11-05 | Prop. 1 unit 50mm Public MSO | Ramonal Village, Camaman-an | not started
100 | 53241.06 | COM2020-056 | 2020-11-05 | Prop. 1 unit 50mm Public MSO | Zone 6A Cugman | not started
101 | 25123.92 | Com2020-57-F | 2020-11-04 | Prop. 1 unit 50mm Public MSO | Zone 9, Cugman | not started
102 | 122022.74 | COM2020-058 | 2020-11-09 | Prop. 1 unit 50mm Public MSO | Zone 6, Tinago Kauswagan | not started
103 | 23168.14 | COM2020-059 | 2020-12-11 | Prop. 1 unit 50mm Public MSO | Samar St. Aluba, Macasandig | not started
104 | 22698.74 | COM2020-060 | 2020-11-12 | Prop. 1 unit 50mm Public MSO | Zone 2. Kauswagan | not started
105 | 54020.1 | COM2020-061 | 2020-11-23 | Prop. 1 unit 50mm Public MSO | 31st st. Nazareth, CDO | not started
106 | 46447.97 | COM2020-062 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Z-6 Capisnon Kaus | not started
107 | 55054.42 | COM2020-063 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Zone 2 Kalye Pogi, Cugman | not started
108 | 24747.29 | COM2020-064 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Purok 6, Urban Poor Asso., Gusa | not started
109 | 24747.29 | COM2020-066 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Zone 1 Igpit Opol | not started
110 | 81294.82 | COM2020-067 | 2020-12-02 | Prop. 1 unit 50mm Public MSO | Zone 4, Bugo | not started
111 | 716398 | 20-075-F | 2020-11-18 | Prop. Replacement of Existing Big Mechanical Meters with 50mmØ Electromagnetic Flowmeters | Limketkai Center | not started
112 | 417195 | 20-079-A | 2020-11-26 | Prop. 75mm Distribution Line w/ 5 MSO | Buara Bayabas | not started
113 | 335811.2 | 20-080-! | 2020-12-02 | Prop. 75mm Pipeline Extension w/ 2 units MSO | Tina-ao, Agusan | not started
114 | 1063244.93 | 20-085 | 2020-12-29 | Prop. Rehabilitation of Roofing & Ceiling | COWD Shop Kaus, CDO | contract out
115 | 2139231 | 20-086 | 2020-12-29 | Prop. Cement Go Down Storage | COWD Shop Kaus, CDO | contract out
116 | 72227 | 20-087 | 2020-12-29 | Prop. Pipeline Interconnection & 1 unit 75mm Meter Assy. w/ chamber | Corrales Extn. Beside Capitol University. CEBU LAND MASTER

## MSO
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
1 | 23896.65 | Com2020-003-F | 2020-01-21 | Prop. 1-Unit 50mmØ Public Stub-out | Sambaan Village, Patag | completed | 1. Transparent, accountable and participatory governance. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth.
2 | 66543.48 | Com2020-004-F | 2020-01-21 | Prop. 1-Unit 50mmØ Public Stub-out | Brgy. 9, Pabayo St. | not started
3 | 66028.24 | Com2020-004-F | 2020-02-05 | Prop. 1-Unit 50mmØ Public Stub-out | JR Borja Extension, Gusa | completed
4 | 132457 | Com2020-005-F | 2020-02-05 | Prop. 1-Unit 50mmØ Public Stub-out | Amfana St., Carmen | not started
5 | 94823.42 | Com2020-006-F | 2020-02-05 | Prop. 1 Unit 50mm Public Stub-out | B3 L2 Ficcoville, Iponan | not started
6 | 113269.05 | Com2020-007-F | 2020-02-14 | Prop. 1 Unit 50mm Public Stub-out | San Isidro Lumbia | completed
7 | 94716.19 | Com2020-009-F | 2020-03-02 | Prop. 1 Unit 50mm Public Stub-out | Zone 1 Igpit Opol | completed
8 | 81100.37 | Com2020-10-F | 2020-02-21 | Prop. 2 Unit 50mm Public Stub-out | Tierra de Puerto, Camaman-an, CDO | completed
9 | 77188.57 | Com2020-011-F | 2020-03-02 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia | completed
10 | 46501.76 | Com2020-012-F | 2020-02-24 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia | completed
11 | 57840 | Com2020-013-F | 2020-03-05 | Prop. 1 Unit 50mm Public Stub-out | Zone 6, Gawad Kalinga Bugo | completed
12 | 48870.74 | Com2020-021-F | 2020-03-31 | Prop. 1 unit Public MSO | Z-10, Bulua | not started
13 | 23238.5 | Com 2020-022-F | 2020-04-02 | Prop. 1 unit Public MSO | Z-4 Basak Pasil Kauswagan | not started
14 | 53490 | Com 2020-023-F | 2020-04-02 | Prop. 1 unit Public MSO | Z-2, Bulua CDO | not started
15 | 830586 | 20-024-F | 2020-03-31 | Prop. 31 units 50mm MSO | Pahiron Relocation Site | not started
16 | 44858.74 | Com2020-024-F | 2020-04-21 | Prop. 1 unit 50mm MSO | Zone 1, Lower Bulua | not started
17 | 173363.4 | 20-028-F | 2020-04-20 | Prop. 50mm Service Line w/ 2 unit MSO | camaman-an, CDO | completed
18 | 21528 | Com2020-25-F | 2020-05-12 | Prop. 1 unit Public MSO | Zone 1, Igpit Opol | completed
19 | 103432 | Com2020-26-F | 2020-05-27 | Prop. 1 unit Public MSO | Bonbon, CDO | not started
20 | 90619 | Com 2020-27-F | 2020-05-27 | Prop. 1 unit Public MSO | Zone 1, Bulua, CDO | not started
21 | 73124.19 | Com 2020-028-F | 2020-07-06 | Prop. 1 unit Public MSO | Zone 3, Barra Opol | not started
22 | 75983.27 | Com2020-29-F | 2020-07-15 | Proposed 3 units 50mm Public MSO | Zone 8, Cugman | Completed
23 | 42092.74 | Com2020-30 | 2020-08-05 | Proposed 1 unit 50mm Public MSO | Mahayah Lumbia
24 | 65831.73 | Com2020-31 | 2020-07-28 | Proposed 3 unit 50mm Public MSO | Lumbia | Completed
25 | 67537 | Com 2020-37-F | 2020-08-27 | Proposed 1 unit 50mm Public MSO | Reyes Cpd. Dist. 5, P-10, Canitoan | not started
26 | 20428.18 | Com 2020-39F | 2020-08-16 | Proposed 1 unit 50mm Public MSO | Z-1, Delima St. Lumbia | completed
27 | 91439 | com2020-047-F | 2020-08-12 | Prop. 50mm MSO | F. Delima St. Lumbia | Completed
28 | 26998.54 | Com2020-32-F | 2020-08-03 | Prop. 1 unit Public MSO | Zone 10, Impantao, Bulua | not started
29 | 75473 | Com2020-33-F | 2020-08-17 | Prop. 1 unit Public MSO | Z-8, Garcia Cpd. Bulua | not started
30 | 77074.1 | Com2020-35-F | 2020-08-17 | Prop. 1 unit Public MSO | Z-7A, Igpit Opol | not started
31 | 77574.11 | Com2020-36-F | 2020-08-17 | Prop. 1 unit Public MSO | Zone 5, Camansi Iponan | not started
32 | 23529.42 | Com2020-034-F | 2020-08-25 | Prop. 1 unit Public MSO | Purok 7 Seaside Gusa | not started
33 | 793700 | 20-049 F | 2020-09-04 | Prop. 50mm Service line w/ 4 units MSO | Malasag Cugman | in-progress
34 | 44247.24 | Com2020-040-F | 2020-09-02 | Prop. 1 unit Public MSO | Z-9, Bulua | not started
35 | 104924 | 20-051-F | 2020-09-07 | Prop. 1 unit Public MSO | Basak Drive Z-4, Pasil Kauswagan | not started
36 | 26053.62 | Com2020-41-F | 2020-09-07 | Prop. 1 unit Public MSO | Ysalina St. Lumbia | completed
37 | 450561 | 20-052-F | 2020-10-30 | Prop. 3 units Public MSO | Apovel subd. Bulua | in-progress
38 | 91150 | 20-053-F | 2020-09-25 | Prop. Transfer of 50mm MSO | Pagatpat Ressetlement Area P-2 Pamalihi, Pagatpat | completed
39 | 96142.74 | Com2020-42-F | 2020-09-21 | Prop. 1 unit 50mm Public MSO | Sambag, Bugo | not started
40 | 122160.23 | Com2020-043-F | 2020-10-01 | Prop. 1 unit 50mm Public MSO | Zone 8, Bugo | not started
41 | 161729.35 | Com2020-044-F | 2020-09-21 | Prop. 1 unit 50mm Public MSO | Ysalina St. Lumbia | completed
42 | 68748.83 | Com2020-045-F | 2020-10-06 | Prop. 2 units 50mm Public MSO | Upper Apovel, Bulua, CDO | completed
43 | 51455.74 | Com2020-046-F | 2020-10-06 | Prop. 1 unit 50mm Public MSO | Z-9, Anhawon, Bulua | not started
44 | 157768.09 | Com 2020-048 | 2020-10-19 | Prop. 1 unit Public MSO | Zone 1 Delima St. Lumbia | not started
45 | 113059.57 | Com 2020-049-F | 2020-10-20 | Prop. 1 unit 50mm MSO | Zone 4, Mahogany Tablon | not started
46 | 48426.15 | Com 2020-050-F | 2020-10-20 | Prop. 1 unit 50mm MSO | Zone 2, Sabalo Lumbia | not started
47 | 28033.47 | Com2020-051-F | 2020-10-30 | Prop. 1 unit 50mm MSO | Zone 8, Lower Bulua | not started
48 | 101828.48 | COM2020-052-F | Oct. 27, 2020 | Prop. 4 units MSO | Zone 7, Agusan, CDO | not started
49 | 93556.74 | COM2020-053-F | 2020-10-27 | Prop. 1 unit MSO | Zone 4, Sarat Agusan | not started
50 | 168106.74 | COM2020-054-F | 2020-11-04 | Prop. 1 unit MSO | Z-1, Sofia Cpd. Bulua
51 | 50329 | 20-073-A | 2020-11-11 | Prop. 25mm Service line Extension | Bagakay, Molave Malasag | not started
52 | 83574.13 | COM2020-055 | 2020-11-05 | Prop. 1 unit 50mm Public MSO | Ramonal Village, Camaman-an | not started
53 | 53241.06 | COM2020-056 | 2020-11-05 | Prop. 1 unit 50mm Public MSO | Zone 6A Cugman | not started
54 | 25123.92 | Com2020-57-F | 2020-11-04 | Prop. 1 unit 50mm Public MSO | Zone 9, Cugman | not started
55 | 122022.74 | COM2020-058 | 2020-11-09 | Prop. 1 unit 50mm Public MSO | Zone 6, Tinago Kauswagan | not started
56 | 23168.14 | COM2020-059 | 2020-12-11 | Prop. 1 unit 50mm Public MSO | Samar St. Aluba, Macasandig | not started
57 | 22698.74 | COM2020-060 | 2020-11-12 | Prop. 1 unit 50mm Public MSO | Zone 2. Kauswagan | not started
58 | 54020.1 | COM2020-061 | 2020-11-23 | Prop. 1 unit 50mm Public MSO | 31st st. Nazareth, CDO | not started
59 | 46447.97 | COM2020-062 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Z-6 Capisnon Kaus | not started
60 | 55054.42 | COM2020-063 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Zone 2 Kalye Pogi, Cugman | not started
61 | 24747.29 | COM2020-064 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Purok 6, Urban Poor Asso., Gusa | not started
62 | 24747.29 | COM2020-066 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Zone 1 Igpit Opol | not started
63 | 81294.82 | COM2020-067 | 2020-12-02 | Prop. 1 unit 50mm Public MSO | Zone 4, Bugo | not started
6349558

## Sheet1
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
1 | 23896.65 | Com2020-003-F | 2020-01-21 | Prop. 1-Unit 50mmØ Public Stub-out | Sambaan Village, Patag | completed | 1. Transparent, accountable and participatory governance. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth.
2 | 66543.48 | Com2020-004-F | 2020-01-21 | Prop. 1-Unit 50mmØ Public Stub-out | Brgy. 9, Pabayo St. | not started
3 | 66028.24 | Com2020-004-F | 2020-02-05 | Prop. 1-Unit 50mmØ Public Stub-out | JR Borja Extension, Gusa | completed
4 | 132457 | Com2020-005-F | 2020-02-05 | Prop. 1-Unit 50mmØ Public Stub-out | Amfana St., Carmen | not started
5 | 94823.42 | Com2020-006-F | 2020-02-05 | Prop. 1 Unit 50mm Public Stub-out | B3 L2 Ficcoville, Iponan | not started
6 | 113269.05 | Com2020-007-F | 2020-02-14 | Prop. 1 Unit 50mm Public Stub-out | San Isidro Lumbia | completed
7 | 94716.19 | Com2020-009-F | 2020-03-02 | Prop. 1 Unit 50mm Public Stub-out | Zone 1 Igpit Opol | completed
8 | 81100.37 | Com2020-10-F | 2020-02-21 | Prop. 2 Unit 50mm Public Stub-out | Tierra de Puerto, Camaman-an, CDO | completed
9 | 77188.57 | Com2020-011-F | 2020-03-02 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia | completed
10 | 46501.76 | Com2020-012-F | 2020-02-24 | Prop. 1 Unit 50mm Public Stub-out | Zone 3 Lumbia | completed
11 | 57840 | Com2020-013-F | 2020-03-05 | Prop. 1 Unit 50mm Public Stub-out | Zone 6, Gawad Kalinga Bugo | completed
12 | 48870.74 | Com2020-021-F | 2020-03-31 | Prop. 1 unit Public MSO | Z-10, Bulua | not started
13 | 23238.5 | Com 2020-022-F | 2020-04-02 | Prop. 1 unit Public MSO | Z-4 Basak Pasil Kauswagan | not started
14 | 53490 | Com 2020-023-F | 2020-04-02 | Prop. 1 unit Public MSO | Z-2, Bulua CDO | not started
15 | 830586 | 20-024-F | 2020-03-31 | Prop. 31 units 50mm MSO | Pahiron Relocation Site | not started
16 | 44858.74 | Com2020-024-F | 2020-04-21 | Prop. 1 unit 50mm MSO | Zone 1, Lower Bulua | not started
17 | 173363.4 | 20-028-F | 2020-04-20 | Prop. 50mm Service Line w/ 2 unit MSO | camaman-an, CDO | completed
18 | 21528 | Com2020-25-F | 2020-05-12 | Prop. 1 unit Public MSO | Zone 1, Igpit Opol | completed
19 | 103432 | Com2020-26-F | 2020-05-27 | Prop. 1 unit Public MSO | Bonbon, CDO | not started
20 | 90619 | Com 2020-27-F | 2020-05-27 | Prop. 1 unit Public MSO | Zone 1, Bulua, CDO | not started
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
21 | 73124.19 | Com 2020-028-F | 2020-07-06 | Prop. 1 unit Public MSO | Zone 3, Barra Opol | not started | 1. Transparent, accountable and participatory governance. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth.
22 | 75983.27 | Com2020-29-F | 2020-07-15 | Proposed 3 units 50mm Public MSO | Zone 8, Cugman | Completed
23 | 42092.74 | Com2020-30 | 2020-08-05 | Proposed 1 unit 50mm Public MSO | Mahayah Lumbia
24 | 65831.73 | Com2020-31 | 2020-07-28 | Proposed 3 unit 50mm Public MSO | Lumbia | Completed
25 | 67537 | Com 2020-37-F | 2020-08-27 | Proposed 1 unit 50mm Public MSO | Reyes Cpd. Dist. 5, P-10, Canitoan | not started
26 | 20428.18 | Com 2020-39F | 2020-08-16 | Proposed 1 unit 50mm Public MSO | Z-1, Delima St. Lumbia | completed
27 | 91439 | com2020-047-F | 2020-08-12 | Prop. 50mm MSO | F. Delima St. Lumbia | Completed
28 | 26998.54 | Com2020-32-F | 2020-08-03 | Prop. 1 unit Public MSO | Zone 10, Impantao, Bulua | not started
29 | 75473 | Com2020-33-F | 2020-08-17 | Prop. 1 unit Public MSO | Z-8, Garcia Cpd. Bulua | not started
30 | 77074.1 | Com2020-35-F | 2020-08-17 | Prop. 1 unit Public MSO | Z-7A, Igpit Opol | not started
31 | 77574.11 | Com2020-36-F | 2020-08-17 | Prop. 1 unit Public MSO | Zone 5, Camansi Iponan | not started
32 | 23529.42 | Com2020-034-F | 2020-08-25 | Prop. 1 unit Public MSO | Purok 7 Seaside Gusa | not started
33 | 793700 | 20-049 F | 2020-09-04 | Prop. 50mm Service line w/ 4 units MSO | Malasag Cugman | in-progress
34 | 44247.24 | Com2020-040-F | 2020-09-02 | Prop. 1 unit Public MSO | Z-9, Bulua | not started
35 | 104924 | 20-051-F | 2020-09-07 | Prop. 1 unit Public MSO | Basak Drive Z-4, Pasil Kauswagan | not started
36 | 26053.62 | Com2020-41-F | 2020-09-07 | Prop. 1 unit Public MSO | Ysalina St. Lumbia | completed
37 | 450561 | 20-052-F | 2020-10-30 | Prop. 3 units Public MSO | Apovel subd. Bulua | in-progress
38 | 91150 | 20-053-F | 2020-09-25 | Prop. Transfer of 50mm MSO | Pagatpat Ressetlement Area P-2 Pamalihi, Pagatpat | completed
39 | 96142.74 | Com2020-42-F | 2020-09-21 | Prop. 1 unit 50mm Public MSO | Sambag, Bugo | not started
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
40 | 122160.23 | Com2020-043-F | 2020-10-01 | Prop. 1 unit 50mm Public MSO | Zone 8, Bugo | not started | 1. Transparent, accountable and participatory governance. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth.
41 | 161729.35 | Com2020-044-F | 2020-09-21 | Prop. 1 unit 50mm Public MSO | Ysalina St. Lumbia | completed
42 | 68748.83 | Com2020-045-F | 2020-10-06 | Prop. 2 units 50mm Public MSO | Upper Apovel, Bulua, CDO | completed
43 | 51455.74 | Com2020-046-F | 2020-10-06 | Prop. 1 unit 50mm Public MSO | Z-9, Anhawon, Bulua | not started
44 | 157768.09 | Com 2020-048 | 2020-10-19 | Prop. 1 unit Public MSO | Zone 1 Delima St. Lumbia | not started
45 | 113059.57 | Com 2020-049-F | 2020-10-20 | Prop. 1 unit 50mm MSO | Zone 4, Mahogany Tablon | not started
46 | 48426.15 | Com 2020-050-F | 2020-10-20 | Prop. 1 unit 50mm MSO | Zone 2, Sabalo Lumbia | not started
47 | 28033.47 | Com2020-051-F | 2020-10-30 | Prop. 1 unit 50mm MSO | Zone 8, Lower Bulua | not started
48 | 101828.48 | COM2020-052-F | Oct. 27, 2020 | Prop. 4 units MSO | Zone 7, Agusan, CDO | not started
49 | 93556.74 | COM2020-053-F | 2020-10-27 | Prop. 1 unit MSO | Zone 4, Sarat Agusan | not started
50 | 168106.74 | COM2020-054-F | 2020-11-04 | Prop. 1 unit MSO | Z-1, Sofia Cpd. Bulua
51 | 50329 | 20-073-A | 2020-11-11 | Prop. 25mm Service line Extension | Bagakay, Molave Malasag | not started
52 | 83574.13 | COM2020-055 | 2020-11-05 | Prop. 1 unit 50mm Public MSO | Ramonal Village, Camaman-an | not started
53 | 53241.06 | COM2020-056 | 2020-11-05 | Prop. 1 unit 50mm Public MSO | Zone 6A Cugman | not started
54 | 25123.92 | Com2020-57-F | 2020-11-04 | Prop. 1 unit 50mm Public MSO | Zone 9, Cugman | not started
55 | 122022.74 | COM2020-058 | 2020-11-09 | Prop. 1 unit 50mm Public MSO | Zone 6, Tinago Kauswagan | not started
56 | 23168.14 | COM2020-059 | 2020-12-11 | Prop. 1 unit 50mm Public MSO | Samar St. Aluba, Macasandig | not started
57 | 22698.74 | COM2020-060 | 2020-11-12 | Prop. 1 unit 50mm Public MSO | Zone 2. Kauswagan | not started
58 | 54020.1 | COM2020-061 | 2020-11-23 | Prop. 1 unit 50mm Public MSO | 31st st. Nazareth, CDO | not started
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
59 | 46447.97 | COM2020-062 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Z-6 Capisnon Kaus | not started | 1. Transparent, accountable and participatory governance. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth.
60 | 55054.42 | COM2020-063 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Zone 2 Kalye Pogi, Cugman | not started
61 | 24747.29 | COM2020-064 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Purok 6, Urban Poor Asso., Gusa | not started
62 | 24747.29 | COM2020-066 | 2020-11-27 | Prop. 1 unit 50mm Public MSO | Zone 1 Igpit Opol | not started
63 | 81294.82 | COM2020-067 | 2020-12-02 | Prop. 1 unit 50mm Public MSO | Zone 4, Bugo | not started
64 | 577789.39 | 20-001-A | 2020-01-13 | Prop. Extension of 100mm Distribution Line, 200mm Distribution Line w/ 75mm Blow Off Valve | Luminarias St., JR Borja Extn. | not started | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth. 4. Transparent, accountable and participatory governance.
65 | 3145906.94 | 20-002-A | 2020-01-13 | Prop. 100mm Pipeline Extension with 14 Units 50mm MSO & DMA | Sitio Tierra Del Puerto, Camaman-an | not started
66 | 1148773.72 | 20-003-A | 2020-01-15 | Prop. Rehabilitation of Water Supply System | Macapaya Phase 1A, Camaman-an | completed
67 | 4487536.04 | 20-004-A | 2020-01-17 | Prop. 200mm Pipeline Extension | Mahogany to Pamalihi Relocation Site | in progress
68 | 550297 | 20-005-F | 2020-01-22 | Prop. 400mm Pipe Realignment | J Seriña St., Carmen | not started
69 | 222459 | 20-006-A | 2020-01-23 | Prop. 150mm Pipeline Realignment | Brgy. Tablon | not started
70 | 468392.64 | 20-008-A | 2020-01-29 | Prop. 100mm UPVC Pipeline Extension with 3 units 50mm Water Meter Stub-out | Caballero & Daing Compound, Zone 7 Bulua | not started
71 | 490481.5 | 20-009-F | 2020-02-05 | Prop. 75mm Pipeline Extension with 4 units 50mm Water Meter Stub-out | Zone 3 Barra Opol | completed
72 | 4601090.25 | 20-010 |  | Prop. Water Supply System | Berjaya, Bugo CDO | completed
73 | 440757 | 20-013-A | 2020-03-15 | Prop. 300mm Pipeline Realignment | Macanhan, Carmen | completed
74 | 1674725 | 20-016-A | 2020-05-16 | Prop. 300mm Temporary Pipeline Realignment | Bigaan Bridge Gusa, CDOC | completed
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
75 | 290910 | 20-017 | 2020-07-10 | Prop. 100mm Distribution Line & Transfer of Existing 75mm BOV | Zone 8 Cugman, CDO | completed | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth. 4. Transparent, accountable and participatory governance.
76 | 50033.74 | 20-019-A | 2020-03-16 | Prop. 300mm Steel Pipe Realignment | Brgy. 24 Osmena St. CDO | completed
77 | 85635.81 | 20-023-F | 2020-03-27 | Prop. 75mm Distribution Line w/ 1 unit MSO | Zone 13, Puli Upper Carmen | not started
78 | 830586 | 20-024-F | 2020-03-31 | Prop. 31 units 50mm MSO | Pahiron Relocation Site | not started
79 | 728352 | 20-031-F | 2020-06-03 | Prop. 500mm & 300mm Pipeline Realignment | Ayesa | completed
80 | 2891341 | 20-033-A | 2020-05-05 | Prop. Realignment of 600mm Steel Pipelines | JR Borja Extn. | not started
81 | 216242 | 20-037-A | 2020-05-15 | Prop. 150mm UPVC Pipeline Interconnection | Buena Oro Macasandig | Completed
82 | 513667.5 | 20-038-F | 2020-06-19 | Prop. 150mm UPVC Pipeline Etension & Interconnection | Buena Oro Macasandig | Completed
83 | 664517 | 20-042-A | 2020-08-05 | Prop. 100mm & 75mmPipeline Extension w/ 2 units MSO | Zone 7, Bulua
84 | 304556 | 20-043-A | 2020-08-04 | Prop. 200mm Realignment | Gaabucayan St., Agora | Completed
85 | 603161.5 | 20-046-A | 2020-08-07 | Prop. 75mm Pipeline extension w/ 2 units 50mm MSO | Across CEO, Kauswagan | not started
86 | 718669 | 20-055-A | 2020-10-05 | Prop. 300mm and 100mm Pipeline Realignment | CM Recto Ave., Lapasan | not started
87 | 4218953 | 17-010-D (PR#19-06-07-0061) | 2017-02-21 | Prop. Expansion of Level 3 WSS forCDORSHP-1 | Phase 3, CDORSHP-1, Talongan Relocation Site, Calaanan | in progress
88 | 841633 | 20-061-A | 2020-11-18 | Prop. 600mm & 400mm Steel Pipeline realignment | Camaman-an Road along Hayes st. ,CDO | not started
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
89 | 320363 | 20-066-A | 2020-10-30 | Prop. 75mm Pipeline Extension w/ 1 unit MSO | Zone 10, Bulua | not started | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth. 4. Transparent, accountable and participatory governance.
90 | 112325 | 20-067-A | 2020-11-20 | Prop. 75mm w/ 1 unit MSO | Zone 7, Bulua | not started
91 | 302862.25 | 20-068-A | 2020-10-30 | Prop. 100mm UPVC Pipe By Pass Line | Silver Creek Phase 1, Canitoan | not started
92 | 248079 | 20-069-A | 2020-11-10 | Prop. 150mm Pipeline Realignment | NHA Phase 2 junction, Kauswagan | in progress
93 | 1597852 | 20-074-f | 2020-11-11 | Prop. 150mm & 100mm Pipeline Extension w/ 6 units MSO | KAHOA, Zone 4 Pasil, Kauswagan | not started
94 | 417195 | 20-079-A | 2020-11-26 | Prop. 75mm Distribution Line w/ 5 MSO | Buara Bayabas | not started
95 | 335811.2 | 20-080-! | 2020-12-02 | Prop. 75mm Pipeline Extension w/ 2 units MSO | Tina-ao, Agusan | not started
96 | 72227 | 20-087 | 2020-12-29 | Prop. Pipeline Interconnection & 1 unit 75mm Meter Assy. w/ chamber | Corrales Extn. Beside Capitol University. CEBU LAND MASTER
97 | 175276 | 20-012-A | 2020-02-06 | Prop. Installation of Data Logger on COBI Pipeline Stub-out | South Diversion Road | not started | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Rapid, inclusive and sustained economic growth. 3. Transparent, accountable and participatory governanace.
98 | 107594.3 | 20-063 | 2020-10-16 | Prop. 75mm BLOW off valve | Capt. V. Roa St. | not started
99 | 3367087.93 | 20-071-D | 2020-11-09 | Prop. Transfer of 350mm Electromagnetic flowmeter | Bugo, Booster | not started
100 | 716398 | 20-075-F | 2020-11-18 | Prop. Replacement of Existing Big Mechanical Meters with 50mmØ Electromagnetic Flowmeters | Limketkai Center | not started
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
101 | 94565 | 20-007-D | 2020-01-28 | Prop. Restoration of Concrete Pavement | Phase 2 Sta. Cecilia Subd., JR Borja Extrn., Camaman-an | completed | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Rapid, inclusive and sustained economic growth. 3. Transparent, accountable and participatory governanace.
102 | 63480 | 20-014-D | 2020-02-24 | Prop. Temporary Fence | PW 31, Ayesa subd. Camaman-an | not started
103 | 216164.75 | 20-021-D | 2020-03-16 | Prop. Rehabilitation of 600mm Electromagnetic Flow Meter Manhole Cover | Take off point Lumbia | not started
104 | 79607 | 20-025-D | 4/220/20 | Prop. Restoration of Concrete Pavement | Poblacion Opol - near Titing's kitchenette | not started
105 | 87446.3 | 20-026-D | 2020-04-20 | Prop. Restoration of Concrete Pavement | Saarenas Rd. Bulua | not started
106 | 79607 | 20-027-D | 2020-04-20 | Prop. Restoration of Concrete Pavement | Opol Highway - (near entrance Roan) | not started
107 |  | 20-039-A |  | Prop. Restoration of Conc. Pavement | Concordio Diel, Zayas Carmen | Completed
108 | 479800 | 20-041-D | 2020-07-15 | Prop. Installation of Railings (3rd flr) and partitons for 2nd & 3rd flr. CR | Tin-ao, Sub-office Bldng. | not started
109 | 406168.83 | 20-048-D | 2020-08-17 | Prop. Steel Formworks & Scaffoldings (for civil work projects) | COWD Shop, Kauswagan | not started
110 | 6252980.22 | 19-037-D | 2020-08-25 | Prop. Elevated Generator stl. Platform | MBSP | in-progress
111 | 83506 | 20-062 | 2020-10-15 | Prop. Restoration of Conc. Pavement | P-2, Sta Cecilia subd. Gusa | not started
112 | 210576 | 20-070-D | 2020-11-09 | Prop. New Chlorine House Storage |  | not started
113 | 716398 | 20-075-F | 2020-11-18 | Prop. Replacement of Existing Big Mechanical Meters with 50mmØ Electromagnetic Flowmeters | Limketkai Center | not started
114 | 1063244.93 | 20-085 | 2020-12-29 | Prop. Rehabilitation of Roofing & Ceiling | COWD Shop Kaus, CDO | contract out
115 | 2139231 | 20-086 | 2020-12-29 | Prop. Cement Go Down Storage | COWD Shop Kaus, CDO | contract out

## pipeline extn, wss, realignment
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | KEY RESULT AREAS
|  | NO. | DATE
1 | 577789.39 | 20-001-A | 2020-01-13 | Prop. Extension of 100mm Distribution Line, 200mm Distribution Line w/ 75mm Blow Off Valve | Luminarias St., JR Borja Extn. | not started | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Poverty reduction and empowerment of the poor and vulnerable. 3. Rapid, inclusive and sustained economic growth. 4. Transparent, accountable and participatory governance.
2 | 3145906.94 | 20-002-A | 2020-01-13 | Prop. 100mm Pipeline Extension with 14 Units 50mm MSO & DMA | Sitio Tierra Del Puerto, Camaman-an | not started
3 | 1148773.72 | 20-003-A | 2020-01-15 | Prop. Rehabilitation of Water Supply System | Macapaya Phase 1A, Camaman-an | completed
4 | 4487536.04 | 20-004-A | 2020-01-17 | Prop. 200mm Pipeline Extension | Mahogany to Pamalihi Relocation Site | in progress
5 | 550297 | 20-005-F | 2020-01-22 | Prop. 400mm Pipe Realignment | J Seriña St., Carmen | not started
6 | 222459 | 20-006-A | 2020-01-23 | Prop. 150mm Pipeline Realignment | Brgy. Tablon | not started
7 | 468392.64 | 20-008-A | 2020-01-29 | Prop. 100mm UPVC Pipeline Extension with 3 units 50mm Water Meter Stub-out | Caballero & Daing Compound, Zone 7 Bulua | not started
8 | 490481.5 | 20-009-F | 2020-02-05 | Prop. 75mm Pipeline Extension with 4 units 50mm Water Meter Stub-out | Zone 3 Barra Opol | completed
9 | 4601090.25 | 20-010 |  | Prop. Water Supply System | Berjaya, Bugo CDO | completed
10 | 440757 | 20-013-A | 2020-03-15 | Prop. 300mm Pipeline Realignment | Macanhan, Carmen | completed
11 | 1674725 | 20-016-A | 2020-05-16 | Prop. 300mm Temporary Pipeline Realignment | Bigaan Bridge Gusa, CDOC | completed
12 | 290910 | 20-017 | 2020-07-10 | Prop. 100mm Distribution Line & Transfer of Existing 75mm BOV | Zone 8 Cugman, CDO | completed
13 | 50033.74 | 20-019-A | 2020-03-16 | Prop. 300mm Steel Pipe Realignment | Brgy. 24 Osmena St. CDO | completed
14 | 85635.81 | 20-023-F | 2020-03-27 | Prop. 75mm Distribution Line w/ 1 unit MSO | Zone 13, Puli Upper Carmen | not started
15 | 830586 | 20-024-F | 2020-03-31 | Prop. 31 units 50mm MSO | Pahiron Relocation Site | not started
16 | 728352 | 20-031-F | 2020-06-03 | Prop. 500mm & 300mm Pipeline Realignment | Ayesa | completed
17 | 2891341 | 20-033-A | 2020-05-05 | Prop. Realignment of 600mm Steel Pipelines | JR Borja Extn. | not started
18 | 216242 | 20-037-A | 2020-05-15 | Prop. 150mm UPVC Pipeline Interconnection | Buena Oro Macasandig | Completed
19 | 513667.5 | 20-038-F | 2020-06-19 | Prop. 150mm UPVC Pipeline Etension & Interconnection | Buena Oro Macasandig | Completed
20 | 664517 | 20-042-A | 2020-08-05 | Prop. 100mm & 75mmPipeline Extension w/ 2 units MSO | Zone 7, Bulua
21 | 304556 | 20-043-A | 2020-08-04 | Prop. 200mm Realignment | Gaabucayan St., Agora | Completed
22 | 603161.5 | 20-046-A | 2020-08-07 | Prop. 75mm Pipeline extension w/ 2 units 50mm MSO | Across CEO, Kauswagan | not started
23 | 718669 | 20-055-A | 2020-10-05 | Prop. 300mm and 100mm Pipeline Realignment | CM Recto Ave., Lapasan | not started
24 | 4218953 | 17-010-D PR#19-06-07-0061 | 2017-02-21 | Prop. Expansion of Level 3 WSS forCDORSHP-1 | Phase 3, CDORSHP-1, Talongan Relocation Site, Calaanan | in progress
25 | 841633 | 20-061-A | 2020-11-18 | Prop. 600mm & 400mm Steel Pipeline realignment | Camaman-an Road along Hayes st. ,CDO | not started
26 | 320363 | 20-066-A | 2020-10-30 | Prop. 75mm Pipeline Extension w/ 1 unit MSO | Zone 10, Bulua | not started
27 | 112325 | 20-067-A | 2020-11-20 | Prop. 75mm w/ 1 unit MSO | Zone 7, Bulua | not started
28 | 302862.25 | 20-068-A | 2020-10-30 | Prop. 100mm UPVC Pipe By Pass Line | Silver Creek Phase 1, Canitoan | not started
29 | 248079 | 20-069-A | 2020-11-10 | Prop. 150mm Pipeline Realignment | NHA Phase 2 junction, Kauswagan | in progress
30 | 1597852 | 20-074-f | 2020-11-11 | Prop. 150mm & 100mm Pipeline Extension w/ 6 units MSO | KAHOA, Zone 4 Pasil, Kauswagan | not started
31 | 417195 | 20-079-A | 2020-11-26 | Prop. 75mm Distribution Line w/ 5 MSO | Buara Bayabas | not started
32 | 335811.2 | 20-080-! | 2020-12-02 | Prop. 75mm Pipeline Extension w/ 2 units MSO | Tina-ao, Agusan | not started
33 | 72227 | 20-087 | 2020-12-29 | Prop. Pipeline Interconnection & 1 unit 75mm Meter Assy. w/ chamber | Corrales Extn. Beside Capitol University. CEBU LAND MASTER
34173180.48

## electro mechanical
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | 5 KRA's
|  | NO. | DATE
1 | 175276 | 20-012-A | 2020-02-06 | Prop. Installation of Data Logger on COBI Pipeline Stub-out | South Diversion Road | not started | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Rapid, inclusive and sustained economic growth. 3. Transparent, accountable and participatory governanace.
3 | 107594.3 | 20-063 | 2020-10-16 | Prop. 75mm BLOW off valve | Capt. V. Roa St. | not started
4 | 3367087.93 | 20-071-D | 2020-11-09 | Prop. Transfer of 350mm Electromagnetic flowmeter | Bugo, Booster | not started
5 | 716398 | 20-075-F | 2020-11-18 | Prop. Replacement of Existing Big Mechanical Meters with 50mmØ Electromagnetic Flowmeters | Limketkai Center | not started

## civil works
CAGAYAN DE ORO CITY WATER DISTRICT
Corrales Avenue, Cagayan de Oro City
ENGINEERING DEPARTMENT
COWD PROJECTS as of December 2020
No. | PROJECT COST | WORK ORDER |  | DESCRIPTION | LOCATION | PROJECT STATUS | 5 KRA's
|  | NO. | DATE
1 | 94565 | 20-007-D | 2020-01-28 | Prop. Restoration of Concrete Pavement | Phase 2 Sta. Cecilia Subd., JR Borja Extrn., Camaman-an | completed | 1. Integrity of the environment and climate change adaptation and mitigation. 2. Rapid, inclusive and sustained economic growth. 3. Transparent, accountable and participatory governanace.
2 | 63480 | 20-014-D | 2020-02-24 | Prop. Temporary Fence | PW 31, Ayesa subd. Camaman-an | not started
2 | 216164.75 | 20-021-D | 2020-03-16 | Prop. Rehabilitation of 600mm Electromagnetic Flow Meter Manhole Cover | Take off point Lumbia | not started
3 | 79607 | 20-025-D | 4/220/20 | Prop. Restoration of Concrete Pavement | Poblacion Opol - near Titing's kitchenette | not started
4 | 87446.3 | 20-026-D | 2020-04-20 | Prop. Restoration of Concrete Pavement | Saarenas Rd. Bulua | not started
5 | 79607 | 20-027-D | 2020-04-20 | Prop. Restoration of Concrete Pavement | Opol Highway - (near entrance Roan) | not started
6 |  | 20-039-A |  | Prop. Restoration of Conc. Pavement | Concordio Diel, Zayas Carmen | Completed
7 | 479800 | 20-041-D | 2020-07-15 | Prop. Installation of Railings (3rd flr) and partitons for 2nd & 3rd flr. CR | Tin-ao, Sub-office Bldng. | not started
8 | 406168.83 | 20-048-D | 2020-08-17 | Prop. Steel Formworks & Scaffoldings (for civil work projects) | COWD Shop, Kauswagan | not started
9 | 6252980.22 | 19-037-D | 2020-08-25 | Prop. Elevated Generator stl. Platform | MBSP | in-progress
10 | 83506 | 20-062 | 2020-10-15 | Prop. Restoration of Conc. Pavement | P-2, Sta Cecilia subd. Gusa | not started
11 | 210576 | 20-070-D | 2020-11-09 | Prop. New Chlorine House Storage |  | not started
12 | 716398 | 20-075-F | 2020-11-18 | Prop. Replacement of Existing Big Mechanical Meters with 50mmØ Electromagnetic Flowmeters | Limketkai Center | not started
13 | 1063244.93 | 20-085 | 2020-12-29 | Prop. Rehabilitation of Roofing & Ceiling | COWD Shop Kaus, CDO | contract out
14 | 2139231 | 20-086 | 2020-12-29 | Prop. Cement Go Down Storage | COWD Shop Kaus, CDO | contract out
11972775.03